House and Senate Public Health, Welfare and Labor Meeting

Arkansas Insurance Department (AID)

Arkansas Health Connector Division (AHC)

Sept. 19, 2013

Update on Marketplace activities

in preparation for Open Enrollment starting October 1, 2013,

and for coverage effective January 1, 2014

Qualified Health Plans Update

- We continue to await U.S. Department of Health and Human Services approval of Qualified Health Plans for Arkansas’s federally-facilitated Health Insurance Marketplace. We will release the final determination of those plans, along with the corresponding rates, at that time.

- AID continues to work with DHS Medicaid, DHS County Operations Division, the Arkansas Center for Health Improvement, health insurance issuers and HP consultants to design the best consumer experience possible for Private Option eligible Arkansans. This work includes segregating the shopping experiences relative to cost sharing for those up to 100 percent of FPL and those above that level, and providing consumers with plan differences for their “shopping consideration”.

Outreach and Education

- The Review Committee voted to advance on the contract amendment for Mangan Holcomb Partners with some modifications, such as the elimination of planned community enrollment activities and a decrease in media buys for the Get Enrolled phase.   The contract amendment, which is funded by our Level One C grant appropriation, was held during the August 7 meeting of the Legislative Review Committee.  It now goes to ALC on Friday. The current contract with MHP runs out September 30.  The addition allows for marketing by MHP during open enrollment which starts October 1—but with $658,000 less than originally requested. It’s imperative to get the word out during open enrollment to help people make the choices that best suit their needs and budgets.

- From July 1 to August 31, there were 214,645 total visits to the website (www.ARHealthConnector.org) including 167,568 unique visitors.

- During July and August more than 152 million media impressions were made across

the state using television, radio, billboards, local newspaper and other media.

- Approximately 140 speakers are expected to have received training by September 23 to participate in the Arkansas Health Connector Speakers Bureau. They will be available for presentations in every county.  There are currently 125 speaking engagements booked through October.

- Following up on our successful call-in educational program on AETN in June, AHCD staff manned the phones at KTHV-Channel 11 in Little Rock on July 25 and on August 27 during newscasts on KARK-Channel 4 in Little Rock. There were nearly 240 calls. Another call-in show was aired on AETN on Sept. 10. There were 104 calls received.  AHCD staff was interviewed and manned the phone bank.

- The AID’s Consumer Services Division (CSD) is prepared to respond to public inquiries that result from our outreach and education efforts.  The CSD reports that in July and August, there were approximately 1,366 phone calls and 174 emails pertaining to the Marketplace. AID has worked diligently to provide answers to all members of the public.

- On August 27, the AID issued a “Consumer Alert” to warn Arkansans about the need to take precautions as enrollment in the Health Insurance Marketplace is scheduled to begin. consumers to be guarded with their personal information, as there may be those hoping to take advantage of any confusion surrounding the details related to the Patient Protection and Affordable Care Act and open enrollment which begins October 1. Any suspicion of fraud should be reported to the AID Consumer Services Division at 800-852-5494.

- The Clinton School of Public Service will be hosting an enrollment event on October 1.

Guides and Other Assisters

- To date, we have 26 contractors for In-Person Assister (IPA) services. A 27th contract is pending with UAMS. Our goal is for IPA entities to employ 537 guides. So far, about 300 guides have completed Phase I training which will transition completely to on-line later this year.  Federal (Phase II) online training is active for all “Assister” types now; our Phase III (Arkansas specific) online is also complete.

- More than 150 people have passed each phase of the training and are awaiting licensing by AID, including 121 agents and brokers and 32 guides.

- AHCD was recently able to contact the New Orleans based organization that received a Navigator grant from HHS. These grants were announced on August 15, 2013. The two grantees for Arkansas are the University of Arkansas Partners for Inclusive Communities ($774,745) and Southern United Neighborhoods ($270,193).  Southern United Neighborhoods (SUN), based out of New Orleans, will also serve Texas and Louisiana. Its Arkansas office is located in Little Rock. We anticipate good cooperation.

- AHCD is working with AID License Division on processes for licensure of guides and other Marketplace assisters, including federal Navigators, certified application counselors, and licensed agents/ brokers to comply with Act 1439 of 2013.  Arkansas Insurance Department Rule 104 sets the annual license fee at $35.  It received a favorable review from the Rules and Regulations Committee and goes before ALC on Friday.

State Partnership Marketplace Evaluation

- AID is pursuing an interagency agreement with UAMS College of Public Health to evaluate the planning and implementation of Arkansas’s State Partnership Health Insurance Marketplace.  There is a commitment by all to coordinate efforts in ongoing performance improvement.

Act 1500

- The first meeting of the Arkansas Health Insurance Marketplace Board was held                September 3 at the University of Arkansas System office in Little Rock. It met again Sept. 12 and will meet a third time on Friday. According to Act 1500 of 2013, the Board will decide whether and when Arkansas should switch from a State Partnership Marketplace to a State-Based Marketplace, upon approval from the U.S. Department of Health and Human Services.

- Sherrill Wise of Little Rock, an executive at Dillard’s Inc., was chosen at the board’s chairperson.

- We have been working with the Bureau of Legislative Research to help relay Marketplace information to legislative staff and Board members.