## Slide 1
Eligibility and Enrollment Framework
Legislative Briefing
May 29th, 2015

## Slide 2
Eligibility and Enrollment Framework (EEF) Project
  Replacement of legacy eligibility System
    Many modules of the system are over 25 years old
    Does not perform automatic eligibility determination
    Incompatible with new Medicaid eligibility rules (referred to as MAGI)
  Implementing new system to:
    Automatically determine eligibility for Medicaid, SNAP, and other Department programs
    Streamline eligibility processes to avoid adding new staff
    Electronically verify benefit rates, increasing accuracy and efficiency
  Project initiated in 2012; MAGI Medicaid came online in 2013
  Current federally-approved project cost is $129.6M
  Current state share of cost for project budget 13.5%

## Slide 3
Vendor Selection and Initial Procurement
  Released systems integrator (general contractor) RFP in early 2012, receiving four bids
  Evaluation committee from DHS, DIS and OSP selected Noridian Systems
  Could not reach agreement with Noridian Systems after months of negotiations
  Time constraints did not allow for new RFP, and state rules precluded moving to the second scoring vendor
  DHS directly engaged subcontractors directly through state staff augmentation contract

## Slide 4
Key Initial Success
  Arkansas was one of the few states to timely and successfully implement a MAGI eligibility system with the basic ability to enroll consumers using the new MAGI rules

## Slide 5: EEF Challenges
Federal System Challenges
  Data errors, system flaws, and other shortcomings in federal data systems have required extensive time, resources, and dollars to overcome
  Federal requirements for state eligibility systems have frequently changed
IBM Cúram Product Limitations
  Significant amount of time, resources, and dollars have been spent customizing the IBM Cúram solution for items that should have been part of the base software solution
Project Management
  Managing multiple subcontractor vendors through separate statements of work
  No single point of authority and responsibility for the project
  Limited options for holding vendors accountable for performance

## Slide 6
Corrective Actions
  After being briefed on the initial review findings, Governor Hutchinson directed DHS to immediately take corrective actions, including:
    Designating a single point of authority within DHS for the project
    Phasing out existing time-and-materials vendor contracts, to be replaced with performance-based, competitively-bid contracts
    Delaying the Traditional Medicaid module to focus on critical needs
    Strengthening statements of work and contract language for existing contracts
    Requiring the Governor's approval for issuance of new contracts or statements of work

## Slide 7
Corrective Actions (Continued)
  In January 2015, DHS removed the lead vendor, EngagePoint, for failure to perform
  DHS is withholding payment of $1.2M until IBM can demonstrate improved Curam functionality and performance
  In April 2015, DHS established an IT Project Management Office with primary oversight of the Enrollment and Eligibility project.

## Slide 8
2015 Successes Following Project Restructure
  System Improvements
    Commencement of eligibility redeterminations and renewals
    Automation of workflow between state and federal systems
    Automated notices for coverage, denials and other items which removed the need for eligibility staff to manually generate notices
    Removal of many system bugs impacting coverage, eligibility determination, and inaccurate denials which significantly reduced the number of manual workarounds, appeals and errors
    Implemented single sign on functionality which allowed eligibility staff and citizens to work through the system without the need to reenter usernames and passwords
    Greatly improved ability to address client “change of circumstance”

## Slide 9
Project Funding
  DHS expects to request an increase from CMS in the federally-approved total project cost this fall, due to:
    Frequently shifting federal requirements
    Challenges with federal Healthcare.gov system
    The uniqueness of Arkansas Medicaid solutions
    IBM Cúram product shortcomings
  Total project cost is projected to be $180 – $220M, which should include integrated functionality for:
    MAGI Medicaid
    Traditional Medicaid (disabled adults and adults over 65)
    SNAP